## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Gantt Chart
PROJECT: Compensation Launch
[5 empty] | Legend: | On track |  |  |  |  | Event |  |  |  |  | Prep |  |  |  |  | Review |  |  |  |  | Unassigned
Project start date: |  | #VALUE! |  |  |  | August | [27 empty] | September
Scrolling increment: |  | 0 | time axis 2026-08-06 to 2026-09-30
Milestone description | Risk | Category | Assigned to | Start | Days | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W
PUBLIC LAUNCH |  |  |  | 2024-09-02 | 10
Volunteer newsletter (forewarning of change) |  | Prep
IT TASKS
Build new pathway for new 16-18 volunteers |  |  | Alex
Create way for existing 12-18yr old volunteers to claim compensation |  |  | Alex
Amend 12-15 pathway |  |  | Alex
Update all consent forms and check against text from REC |  |  | Alex
Test process |  |  | Alex
Update graphics on www.gen.scot (e.g. showing steps to join) |  |  | Alex/Elly
Create gen.scot page explaining compensation (if EdWeb page can't be created easily) |  |  | Alex/comms
Recontact #1: Email to existing volunteers eligible for voucher |  |  | Alex/Archie
Recontact #2: email to existing vols eligible for voucher who haven't completed questionnaire |  |  | Alex/Archie
Recontact #3: email to existing vols eligible for voucher who haven't returned sample |  |  | Alex/Archie
Updates to chaser emails |  |  | Alex
COMMS TASKS
Poster and leaflet designs (decide audiences then design) |  | Prep | Sarah/Rosie | 2024-07-15 | 10
Video design for locations (e.g. unis) and/or social media |  | Prep | Elly/Zhuoni
Create animation explaining why we're doing compensation |  | Prep | Elly/Zhuoni
Create comms pack (asking to share on socials, in newsletters etc) |  | Prep | Elly/Rosie
Distribute comms pack (remember to track distribution) |  | Prep | Fiona/Rosie
Decide locations for promotion (e.g. universities, NHS, opticians) |  | Prep | Rosie/Fiona
Coordinate Freshers presence |  | Prep | Rosie/Fiona
Updating schools (coordinate timing with end of school holidays) |  | Prep | Sarah/Fiona
Add dedicated page and FAQ to .ed.ac.uk website |  | Prep | Elly/Leah
Contact UoE comms/Press Office about launch |  | Prep | Fiona
Mental Health Youth Forum: highlight upcoming compensation in slides |  | Event | Sarah | 2024-07-23 | 1 | T: Posters
Update gen.scot text |  | Prep | Sarah/Fiona/Alex
Prepare social media content and schedule |  | Prep | Elly/Rosie
Link in with lesson plans (circulate leaflets through SHINE) |  | Prep | Sarah/Anne/Heather
Send posters to Clarissa (Sarah contact - nursing students contact) for Freshers Week |  | Prep | Sarah/Rosie | 2024-07-23 | 1
Get quote from Heather, Cathie, Anna and/or Andrew Morris about teen compensation |  | Prep | Robin
Update social media and website banner to reflect new steps to joining (incl. 12-15 process + 12-18 compensation) |  | Prep | Rosie
ETHICS TASKS
Cathie to check NHS posters/videos |  | Event | Comms/Cathie
Submit NHS posters/videos to ethics |  | Event | Liz
ADMIN TASKS
Determine list of stakeholders to contact with comms pack |  | Prep | Fiona
Prioritisation of audiences/comms channels/stakeholders |  | Prep | Fiona/Sarah
Raise at Scientific Steering Committee Meeting |  | Prep | Liz/Heather
Buy vouchers |  | Prep | Liz
Train Fiona, Robin and Leah in how to buy vouchers |  | Prep | Liz
To add more data, Insert new rows ABOVE this one |  | Event

## Sheet1
Goal
Milestone
Event
Prep